STANDIT

MVP EXECUTION ROADMAP

4 Phases  |  10 Weeks  |  4-Person Core Team

Version 1.0  —  March 2026

Field

Value

Document Type

MVP Production Execution Roadmap

Total Duration

10 weeks (prototype through launch-hardened MVP)

Core Team

4 engineers: 1 backend, 1 frontend/game, 1 full-stack, 1 animator

Support

0.5 sound designer (weeks 3–8), 0.5 QA (weeks 5–10)

Output

Production-deployed 2D web crash game with provably fair RNG, MMA tension visuals, wallet integration

Companion Docs

GDD v1.0, Frontend Arch v1.0, Animation System v1.0, UI/UX Spec v1.0, Backend Contract v1.0

1. Roadmap Overview

1.1 Phase Summary

Phase

Name

Weeks

Goal

Exit Criteria

Phase 1

Prototype

Weeks 1–3

Prove the round engine and tension-to-visual pipeline work end-to-end in a browser.

A single player can place a bet, watch a tension-driven fight scene, cash out or bust, and see a provably fair result. No wallet, no auth, no polish.

Phase 2

Playable Internal MVP

Weeks 4–6

A multiplayer crash game with real visuals, sound, and the full round lifecycle running on a staging server.

5+ concurrent players in a shared room. Full animation library (MVP set). Sound. Mobile-responsive. Internal team plays daily.

Phase 3

Operator-Ready MVP

Weeks 7–8

Integrate wallet, auth, admin config, fairness verification, and error handling.

Real money flow (test wallet). Admin can configure room. Provably fair verification page works. Error states handled. Ready for QA.

Phase 4

Launch Hardening

Weeks 9–10

Stress test, security audit, performance optimization, and deployment pipeline.

Load tested at 500 concurrent connections. Security review passed. Monitoring and alerts live. Deployment playbook documented. Go/no-go checklist complete.

1.2 Team Allocation

Role

Person

Weeks 1–3

Weeks 4–6

Weeks 7–8

Weeks 9–10

Backend Engineer

BE

Round engine, WS protocol, crash logic

Multi-room, settlement, live feed

Wallet integration, admin API, audit log

Load testing, security hardening

Frontend / Game Engineer

FE

Phaser scene, tension pipeline, React shell

Full UI, animation integration, mobile layout

Error states, reconnect, fairness modal

Performance optimization, fallback modes

Full-Stack Engineer

FS

WS client, state stores, multiplier clock

Sound integration, history, live bets

Auth integration, deployment, CI/CD

Monitoring, alerts, deployment playbook

2D Animator

ART

3 placeholder clips (box fighters)

MVP clip set (18 clips, ~840 frames)

Crash variants, polish, sprite sheet optimization

Bug fixes, final asset delivery

Sound Designer

SND

—

Tension layers, crash hit, cashout chime

Polish, audio sprite packaging

—

QA

QA

—

—

Functional testing, edge cases, mobile testing

Regression, load testing support, launch sign-off

2. Phase 1: Prototype (Weeks 1–3)

PHASE GOAL

Prove three things: (1) the round engine works correctly with provably fair crash points, (2) the tension-to-animation pipeline produces the intended emotional arc, and (3) Phaser + React coexist at 60fps on mobile. Nothing else matters in Phase 1.

2.1 Milestone: M1 — Round Engine Running (End of Week 1)

Task ID

Task

Owner

Days

Dependencies

Deliverable

BE-001

Scaffold Go game server with WebSocket support

BE

1

None

Server accepts WS connections, echoes messages

BE-002

Implement round state machine (BETTING → RUNNING → CRASHED → SETTLED)

BE

2

BE-001

Round cycles through phases on a timer

BE-003

Implement crash point generation (provably fair, HMAC-SHA256 seed chain)

BE

1

None

Deterministic crash points from seed, verifiable

BE-004

Implement multiplier curve (exponential, configurable speed constant)

BE

0.5

BE-002

Multiplier climbs and triggers crash at crash_point

BE-005

Implement bet placement and cashout (in-memory, no wallet)

BE

1.5

BE-002, BE-004

Player can bet, cashout, or bust. Payout computed.

FE-001

Scaffold Vite + React + TypeScript project

FE

0.5

None

Dev server running, hot reload

FE-002

Create Zustand stores (gameStore, playerStore)

FS

1

FE-001

Stores with typed state and actions

FE-003

Build WSClient + MessageRouter + binary codec

FS

2

FE-001, BE-001

Client connects to server, dispatches to stores

FE-004

Build MultiplierClock (client-side interpolation)

FS

1

FE-002, FE-003

60fps multiplier from 10Hz server ticks

2.2 Milestone: M2 — Visual Pipeline Proven (End of Week 2)

Task ID

Task

Owner

Days

Dependencies

Deliverable

FE-005

Initialize Phaser 3 in React container (PhaserContainer component)

FE

0.5

FE-001

Phaser canvas renders inside React layout

FE-006

Build ArenaScene with layer hierarchy (bg, cage, fighters, fx-overlay)

FE

1

FE-005

Static cage scene visible in browser

FE-007

Build TensionMapper (multiplier → tension curve)

FE

0.5

FE-002

Tension value 0.0–1.0 derived from multiplier

FE-008

Build FighterController with placeholder sprites (colored rectangles)

FE

1.5

FE-006, FE-007

Two rectangles animate based on tension band

FE-009

Build EnvironmentFX (vignette, camera shake, color tint)

FE

1

FE-006, FE-007

Environmental effects respond to tension

FE-010

Build CrashSequence (freeze, flash, collapse placeholder, dim)

FE

1

FE-008, FE-009

Crash visually interrupts the scene

FE-011

Build CashoutFX (green flash, desaturate)

FE

0.5

FE-009

Cashout feedback plays on the scene

ART-001

Design fighter silhouette style guide (2 character sheets)

ART

2

None

Pro + amateur character designs approved

ART-002

Produce 3 placeholder clips (1 per band A/B/C) as sprite sheets

ART

3

ART-001

Real sprites replace colored rectangles

2.3 Milestone: M3 — End-to-End Prototype (End of Week 3)

Task ID

Task

Owner

Days

Dependencies

Deliverable

FE-012

Build React UI shell: MultiplierDisplay, BetPanel, CashoutButton

FS

2

FE-002, FE-004

Player can bet and cashout via UI

FE-013

Build RoundHistory strip (colored pills)

FS

0.5

FE-002

Last 20 crash points visible

FE-014

Wire Phaser store subscription (ArenaScene reads tension from store)

FE

1

FE-006, FE-007, FE-003

Phaser reacts to server state changes

FE-015

Integrate real sprites from ART-002 into FighterController

FE

1

FE-008, ART-002

Real fighter art in the scene

FE-016

Mobile-responsive layout (portrait primary)

FS

1

FE-012

Playable on mobile viewport

BE-006

Implement MULTIPLIER_TICK broadcast (10Hz to all clients)

BE

0.5

BE-004

Clients receive periodic multiplier updates

BE-007

Implement LIVE_BET and LIVE_CASHOUT broadcasts

BE

0.5

BE-005

Social feed events broadcast to room

INT-001

Full integration test: place bet → watch fight → cashout or bust → see result

ALL

1

All above

Single-player prototype works end-to-end

PHASE 1 EXIT GATE

One person opens the game on their phone, places a fake bet, watches tension-driven fighter animations rise with the multiplier, taps cashout (or watches the crash), and sees the result. The provably fair verification can be checked manually via the server’s console output. If this works, Phase 1 is complete.

3. Phase 2: Playable Internal MVP (Weeks 4–6)

PHASE GOAL

Transform the prototype into a game the internal team plays daily. Full MVP animation set, sound design, multiplayer with live feed, and mobile polish. The game must feel real even though wallet and auth are still mocked.

3.1 Milestone: M4 — Full Animation + Sound (End of Week 4)

Task ID

Task

Owner

Days

Dependencies

Deliverable

ART-003

Produce MVP animation clips: 18 clips (A: 3, B: 4, C: 4, D: 4, X: 2, shared neutral pose)

ART

10

ART-001

~840 frames delivered as WebP sprite atlases + JSON manifests

ART-004

Generate mirrored sprite sheets (automated at build time)

ART

0.5

ART-003

Mirror variants for all mirrorable clips

FE-017

Integrate full MVP clip library into FighterController

FE

2

ART-003, FE-008

All 18 clips playing correctly per tension band

FE-018

Implement clip selection algorithm (CosmeticRNG, no-repeat, band transitions)

FE

1

FE-017

Clips chain smoothly with no visible seams

FE-019

Implement speed variation (0.85x / 1.0x / 1.15x per tension position)

FE

0.5

FE-018

Same clip feels different at different tension levels

SND-001

Produce audio sprite sheet: tension drone, heartbeat, crowd layers, crash hit, cashout chime, coin settle

SND

5

None

Single audio file + manifest delivered

FE-020

Build AudioManager + TensionMixer (Howler.js, 4 layers, tension-driven mixing)

FS

2

SND-001

Sound layers respond to tension value in real time

3.2 Milestone: M5 — Multiplayer + UI Complete (End of Week 5)

Task ID

Task

Owner

Days

Dependencies

Deliverable

BE-008

Multi-player room management (join, leave, player count tracking)

BE

2

BE-002

Multiple WS clients in same room

BE-009

Implement round result broadcast (per-player outcome)

BE

1

BE-005

Each player gets personalized ROUND_RESULT

BE-010

Implement auto-cashout (server-side, zero latency)

BE

1

BE-005

Bets with auto_cashout_at are settled by server

FE-021

Build LiveBets feed component (other players’ bets and cashouts)

FS

1

FE-003, BE-007

Social proof visible in info tray

FE-022

Build full BetPanel (presets, custom input, ×2/÷2, bet persistence)

FS

1.5

FE-012

Full betting UI per UI/UX spec

FE-023

Build CashoutButton with live win amount, processing state, double-tap protection

FE

1

FE-012

Cashout button per UI/UX spec

FE-024

Implement phase transitions (BetPanel ↔ CashoutButton swap, animations)

FS

1

FE-022, FE-023

Smooth 300–400ms transitions between phases

FE-025

Build WalletBar (balance display, connection indicator)

FS

0.5

FE-002

Status bar shows balance and connection state

FE-026

Implement multiplier color progression (white → gold → red via ref-based update)

FE

0.5

FE-004

60fps color-coded multiplier per UI/UX spec

3.3 Milestone: M6 — Internal Playtest Ready (End of Week 6)

Task ID

Task

Owner

Days

Dependencies

Deliverable

FE-027

Build ResultToast (win/loss notification with animation)

FS

0.5

FE-002

Win: green floating amount. Loss: muted red text.

FE-028

Implement cashout button glow/pulse escalation per multiplier

FE

0.5

FE-023

Button visually intensifies with tension

FE-029

Particle system (dust/sparks, object-pooled, tension > 0.4)

FE

1

FE-006

Particles add depth to high-tension scenes

FE-030

Desktop layout (center arena + right sidebar controls)

FS

1

FE-016

Playable on desktop browsers

FE-031

Asset loading pipeline (BootScene → PreloadScene → ArenaScene with progress bar)

FE

1

FE-005, ART-003

3-phase loading with visible progress

BE-011

Implement TimeSync handshake (3-sample NTP-like exchange)

BE

1

BE-001

Client-server clock sync within 20ms

BE-012

Implement seed chain and seed_hash pre-commitment

BE

1

BE-003

Each round publishes seed hash before betting opens

INT-002

Internal playtest: 5+ team members, 30-min sessions, bug triage

ALL

2

All Phase 2 tasks

Bug list prioritized. Feel assessment documented.

PHASE 2 EXIT GATE

Five team members play simultaneously for 30 minutes on their phones. The game feels like a real product: fighters animate smoothly, sound builds tension, cashout/crash feedback is satisfying, and the social feed shows others’ activity. Bugs are logged but no critical blockers remain. The team genuinely wants to keep playing.

4. Phase 3: Operator-Ready MVP (Weeks 7–8)

PHASE GOAL

Connect the game to real infrastructure: wallet service, authentication, admin configuration, fairness verification, and robust error handling. The game transitions from a toy to a deployable product.

4.1 Milestone: M7 — Infrastructure Integration (End of Week 7)

Task ID

Task

Owner

Days

Dependencies

Deliverable

BE-013

Wallet service integration: lock_funds, settle_win, consume_lock (idempotent, with retry)

BE

3

BE-005

Real money flow through test wallet

BE-014

Auth integration: JWT validation on WS handshake, player_id extraction

BE

1

BE-001

Only authenticated users can join rooms

BE-015

Admin REST API: room config CRUD, pause/resume, audit endpoint

BE

2

BE-002

Operator can configure rooms via API

BE-016

Implement RoomConfig hot-reload (changes apply at next round)

BE

0.5

BE-015

Config changes without server restart

BE-017

Implement round audit log (immutable, append-only, per Backend Contract spec)

BE

1.5

BE-002, BE-005

Every round produces a full audit record

FE-032

Auth flow integration (token refresh, session management)

FS

1

BE-014

Player authenticates before joining

FE-033

Balance from wallet (real balance display, update on bet/cashout)

FS

1

BE-013, FE-025

Balance reflects actual wallet state

FE-034

Build FairnessModal (seed display, hash verification, external link)

FS

1

BE-012, FE-013

Player can verify any completed round

4.2 Milestone: M8 — Error Handling + Reconnect (End of Week 8)

Task ID

Task

Owner

Days

Dependencies

Deliverable

FE-035

Implement all error states per UI/UX spec (insufficient balance, bet limits, wallet unavailable, cashout denied)

FS

1.5

FE-022, FE-023

Every error has inline or toast feedback

FE-036

Build reconnect overlay (connection status, retry with backoff, active bet messaging)

FE

1.5

FE-003

Player sees clear state during disconnection

FE-037

Implement ROOM_STATE reconnect handler (snap to current state without replay)

FS

1

FE-003, FE-014

Reconnect restores full game state instantly

BE-018

Implement PlayerSession takeover on reconnect (stale session cleanup)

BE

1

BE-001

Reconnecting player takes over old session

BE-019

Implement active bet resolution on disconnect (MVP: ride to crash)

BE

0.5

BE-005, BE-018

Disconnected bets are settled correctly

FE-038

Implement prefers-reduced-motion (disable shake, pulse, particles)

FE

0.5

FE-009

Accessibility compliance

FE-039

Responsible gambling timer (15-min session reminder)

FS

0.5

FE-002

Non-dismissable reminder at 15-min intervals

QA-001

Functional test pass: all round phases, bet flows, cashout flows, crash, reconnect, error states

QA

3

All Phase 3 tasks

Test report with pass/fail per scenario

QA-002

Mobile device testing: iOS Safari, Android Chrome, Samsung Internet (top 5 devices)

QA

2

FE-016

Device compatibility report

PHASE 3 EXIT GATE

The game runs against a test wallet with real balance operations. An admin can configure room settings via API. A player can verify any round’s fairness. All error states display correctly. Reconnection works mid-round. QA has completed a full functional test pass with no P0 or P1 bugs open.

5. Phase 4: Launch Hardening (Weeks 9–10)

PHASE GOAL

Make the game production-safe. Stress test, security audit, performance optimization, monitoring, and a deployment pipeline that the team trusts. The exit gate is a go/no-go decision for production traffic.

5.1 Milestone: M9 — Performance + Security (End of Week 9)

Task ID

Task

Owner

Days

Dependencies

Deliverable

BE-020

Load test: simulate 500 concurrent WS connections, 50 bets per round, 10Hz tick broadcast

BE

2

All backend

Load test report: p50/p95/p99 latencies, memory, CPU, failure rate

BE-021

Security review: WS auth bypass attempts, rate limiting, input validation, seed exposure testing

BE

2

All backend

Security review report with remediation

BE-022

Rate limiting on WS messages (per-client, per-message-type)

BE

1

BE-001

Bots and spammers throttled

FE-040

Performance audit: Lighthouse score, frame time profiling, memory leak check (30-min session)

FE

1.5

All frontend

Performance report with before/after metrics

FE-041

Implement PerformanceMonitor + auto quality scaling (High → Medium → Low)

FE

1

FE-009, FE-029

Auto-degrade on slow devices

FE-042

Service worker for asset caching (Workbox, cache-first strategy)

FS

1

FE-031

Return visits load from cache. Offline shell.

FE-043

Bundle size audit: ensure shell < 60KB gzip, game chunk < 250KB gzip

FS

0.5

All frontend

Bundle analysis report

ART-005

Final sprite sheet optimization: trim whitespace, palette reduction, WebP compression

ART

1

ART-003

Sprite assets < 3MB total (Phase 1 budget)

5.2 Milestone: M10 — Deployment + Launch Gate (End of Week 10)

Task ID

Task

Owner

Days

Dependencies

Deliverable

FS-001

Production deployment pipeline: CI/CD, staging → production promotion, rollback capability

FS

2

All code

One-command deploy with automated tests

FS-002

Monitoring stack: Prometheus metrics, Grafana dashboards, alerting rules per Backend Contract

FS

2

BE-020

Dashboard live with all 12 metrics + 7 alert rules

FS-003

Structured logging pipeline: JSON logs → ELK/Datadog, 17 event types indexed

FS

1

BE-017

Logs searchable and queryable in production

BE-023

Implement crash point distribution verification (KS-test over 1000 rounds in staging)

BE

0.5

BE-003

Statistical proof that RNG distribution is correct

QA-003

Full regression test: all P1/P2 bugs from Phase 3 verified fixed

QA

1.5

QA-001

Regression report: all clear

QA-004

End-to-end test: 10 concurrent players, 50 rounds, real wallet (staging), provably fair verification of every round

QA

1.5

All tasks

E2E test report: 100% rounds verified

ALL-001

Launch checklist review (see Section 7)

ALL

0.5

All tasks

Every checklist item signed off

PHASE 4 EXIT GATE

Load test confirms 500 concurrent connections at < 100ms p95 cashout latency. Security review has no open critical or high findings. Monitoring dashboards show healthy metrics on staging. KS-test confirms crash distribution matches expected. Go/no-go meeting produces a GO decision.

6. Critical Path and Dependencies

6.1 Critical Path

The critical path — the longest chain of dependent tasks that determines the minimum project duration — runs through the animation pipeline. Art production is the single biggest schedule risk.

CRITICAL PATH (calendar time):

Week 1:  ART-001 (fighter style guide)           [2 days]

|

Week 2:  ART-002 (3 placeholder clips)            [3 days]

|

Week 2:  FE-015 (integrate real sprites)           [1 day]

|

Week 3:  INT-001 (e2e prototype integration)       [1 day]

|

Week 4–6: ART-003 (18 MVP clips, ~840 frames)     [10 days] ← BOTTLENECK

|

Week 5:  FE-017 (integrate full clip library)      [2 days]

|

Week 6:  INT-002 (internal playtest)               [2 days]

Total critical path: ~21 working days

MITIGATION: ART-003 parallelizes with backend and UI work.

If art runs late by up to 3 days, it delays Phase 2 exit

but does NOT block Phase 3 (backend/UI work continues).

6.2 Parallel Work Streams

The project runs four parallel tracks that converge at integration milestones:

Track

Owner

Weeks 1–3

Weeks 4–6

Weeks 7–8

Weeks 9–10

Game Server

BE

Round engine + WS protocol

Multi-room + settlement

Wallet + admin + audit

Load test + security

Game Client (Phaser)

FE

Scene + tension pipeline + FX

Full animation integration

Reconnect + accessibility

Performance + fallback

UI + Network (React)

FS

Stores + WS client + UI shell

Full UI + sound + history

Auth + errors + deploy

Monitoring + CI/CD

Art Production

ART

Style guide + 3 placeholders

18 MVP clips (full sprint)

Polish + optimization

Final delivery

7. Launch Checklist

Every item must be signed off before production traffic. No exceptions. Items are grouped by category and ordered by criticality.

7.1 Game Integrity

#

Item

Verified By

Status

G-01

Crash point distribution matches expected (KS-test, p > 0.05, N=1000)

BE + QA

[ ]

G-02

Provably fair verification works: any player can verify any completed round

QA

[ ]

G-03

Seed chain is pre-committed: hash published before round, seed revealed after

BE + QA

[ ]

G-04

Animation system has zero knowledge of crash point (code review confirmed)

FE + BE

[ ]

G-05

Cashout race condition handled: server-authoritative, denied if crash happened first

BE + QA

[ ]

G-06

House edge matches configured value (verified over 1000+ test rounds)

BE + QA

[ ]

7.2 Money Handling

#

Item

Verified By

Status

M-01

Wallet lock-on-bet: funds reserved before round starts, never double-charged

BE + QA

[ ]

M-02

Wallet settle-on-cashout: payout credited atomically with bet settlement

BE + QA

[ ]

M-03

Wallet consume-on-bust: locked funds consumed, not silently lost

BE + QA

[ ]

M-04

All wallet operations are idempotent (retry-safe with unique transaction IDs)

BE

[ ]

M-05

max_win cap enforced: no payout exceeds configured maximum

BE + QA

[ ]

M-06

Balance never goes negative under any race condition

BE + QA

[ ]

M-07

Wallet service failure degrades gracefully: bets rejected, cashouts queued

BE + QA

[ ]

7.3 Security

#

Item

Verified By

Status

S-01

WS authentication: invalid/expired tokens rejected at handshake

BE + QA

[ ]

S-02

Rate limiting: cashout requests, bet requests, connection attempts

BE + QA

[ ]

S-03

Input validation: all numeric inputs bounded, no SQL/NoSQL injection vectors

BE

[ ]

S-04

Crash point never transmitted to client before crash event

BE + FE (code review)

[ ]

S-05

Server seed never exposed before round ends

BE (code review + test)

[ ]

S-06

WS messages authenticated per-session (no session hijacking)

BE

[ ]

S-07

Admin endpoints require elevated auth (separate from player auth)

BE

[ ]

7.4 Performance

#

Item

Verified By

Status

P-01

500 concurrent WS connections sustained without degradation

BE + QA

[ ]

P-02

Cashout latency < 100ms p95 under load

BE + QA

[ ]

P-03

Multiplier tick broadcast < 50ms to all clients in room

BE

[ ]

P-04

Client TTI < 3s on 4G (Lighthouse CI)

FE + QA

[ ]

P-05

60fps sustained on Samsung Galaxy A13 (2022) during gameplay

FE + QA

[ ]

P-06

No memory leaks over 30-minute session (JS heap stable)

FE + QA

[ ]

P-07

Sprite assets < 3MB total. Audio < 1.5MB. JS bundle < 320KB gzip.

FE

[ ]

7.5 Observability

#

Item

Verified By

Status

O-01

All 17 structured log events firing correctly in production

FS + QA

[ ]

O-02

All 12 Prometheus metrics reporting to Grafana dashboard

FS

[ ]

O-03

All 7 alert rules configured and tested (at least 1 fire-drill per alert)

FS

[ ]

O-04

Audit log writing to append-only storage with correct retention

BE + FS

[ ]

O-05

Error rates visible in real-time dashboard

FS

[ ]

7.6 Compliance and UX

#

Item

Verified By

Status

C-01

Responsible gambling timer fires at 15-minute intervals

QA

[ ]

C-02

House edge and RTP displayed (where required by jurisdiction)

QA

[ ]

C-03

Provably fair page publicly accessible

QA

[ ]

C-04

No blood, no impact, no knockout depicted (content review)

ART + QA

[ ]

C-05

WCAG AA contrast on all interactive elements

FE + QA

[ ]

C-06

prefers-reduced-motion suppresses shake, pulse, particles

FE + QA

[ ]

C-07

All error states display correctly per UI/UX spec

QA

[ ]

C-08

Reconnect mid-round works: state restored, bet resolved

QA

[ ]

7.7 Deployment

#

Item

Verified By

Status

D-01

CI/CD pipeline runs: lint, test, build, deploy to staging, smoke test

FS

[ ]

D-02

Staging environment mirrors production (same infra, same config)

FS

[ ]

D-03

Rollback procedure tested: can revert to previous version in < 5 minutes

FS

[ ]

D-04

Database migrations are backward-compatible (no breaking schema changes)

BE + FS

[ ]

D-05

SSL/TLS configured for HTTPS and WSS

FS

[ ]

D-06

Domain and DNS configured

FS

[ ]

D-07

On-call rotation defined for first 2 weeks post-launch

ALL

[ ]

8. Risk Register

Risk

Likelihood

Impact

Mitigation

Owner

Art production takes longer than 10 days (ART-003)

Medium

High (delays Phase 2 exit)

Start art in Week 1 (style guide). Use placeholder sprites for all non-art work. Art pipeline can slip 3 days without blocking Phase 3.

ART

Wallet service integration is more complex than expected

Medium

Medium (delays Phase 3)

Define wallet API contract in Week 1. Mock wallet in Phases 1–2. Integrate real wallet as a swap, not a rewrite.

BE

Phaser + React performance conflict on low-end mobile

Low

High

Phase 1 prototype tests on Galaxy A13 immediately. If issues found, address before art investment. Auto quality scaling is built in Phase 4.

FE

Cashout latency perceived as unfair by players

Medium

High (trust)

Server-authoritative cashout with clear UX: processing state, denied explanation. Auto-cashout (Phase 2) eliminates latency concern for disciplined players.

BE + FE

Regulatory classification as simulated sporting event

Low

Critical

Fighters are abstract/masked. No simulated match outcome. All marketing says “crash game.” Legal review before public launch.

ALL

Sound designer unavailable for Weeks 4–6

Low

Medium

Use royalty-free placeholder sounds. Replace with custom audio in Phase 3 if necessary. Game is playable without custom sound.

SND

Single-point-of-failure: one backend server

Medium

High in prod

Acceptable for MVP. Redis state snapshot enables fast recovery. Phase 4 load test validates single-server capacity. Multi-server is Launch scope.

BE

9. Task Count Summary

Category

Phase 1

Phase 2

Phase 3

Phase 4

Total

Backend (BE)

7

5

7

4

23

Frontend / Game (FE)

11

6

4

4

25

Full-Stack (FS)

4

5

5

3

17

Art (ART)

2

2

0

1

5

Sound (SND)

0

1

0

0

1

QA

0

0

2

2

4

Integration (INT/ALL)

1

1

0

1

3

TOTAL

25

20

18

15

78

78 tasks across 10 weeks, averaging 7–8 tasks per week across the team. Peak density is Weeks 4–6 (Phase 2) where animation integration, sound, and multiplayer converge. The schedule has ~1 week of buffer absorbed across phases (tasks estimated at 80% confidence, not 50%).

END OF DOCUMENT

STANDIT MVP Execution Roadmap v1.0 — Confidential